## Sheet1
Phase | Stage | Task | Task Assignee | Notes | Deadline | Date of Completion | Reason for Delay | Action Taken | Git Commit Tag | Completion Date Coloring Schema:
Phase 1 | Stage 0: Planning and Orginization | Standards Finalization |  |  | 2020-06-29 |  |  |  |  | Done ahead of schedule
|  | Jira Setup | Devon | [6 empty] | Done on schedule
|  | GITHUB Setup & Link to Jira | Harry | [6 empty] | Done behind schedule
|  | Code Review and MISRA SetUp | [7 empty] | To Do
| Stage 1: System Specifications | High Level System Specifications | Waseem, Antonio |  | 2020-07-01 |  |  |  |  | Overdue
|  | Module Level Functional Descriptions | Waseem, Antonio
UVM Research
| Stage 2: Requirements Generation | Top Level Design & DCM Requirements |  | Reviewed by: | 2020-07-10
|  | Wishbone IF Requirements |  | Reviewed by:
|  | Synchronous FIFO Requirements |  | Reviewed by:
|  | Tx Priority Logic Requirements |  | Reviewed by:
|  | Acceptance Filter Requirements |  | Reviewed by:
|  | Register Bank Requirements |  | Reviewed by:
|  | Bitstream Processor Requirements |  | Reviewed by:
|  | Bit Timing Module Requirements |  | Reviewed by:
| Stage 3: Test Cases Generation | Top Level Design & DCM Test Cases |  | Reviewed by:
|  | Wishbone IF Test Cases |  | Reviewed by:
|  | Synchronous FIFO Test Cases |  | Reviewed by:
|  | Tx Priority Logic Test Cases |  | Reviewed by:
|  | Acceptance Filter Test Cases |  | Reviewed by:
|  | Register Bank Test Cases |  | Reviewed by:
|  | Bitstream Processor Test Cases |  | Reviewed by:
|  | Bit Timing Module Test Cases |  | Reviewed by:
Phase 2 | Stage 4: Module Development & Validation | Wishbone IF Development |  | Reviewed by: | 2020-07-16
|  | Synchronous FIFO Development |  | Reviewed by:
|  | Tx Priority Logic Development |  | Reviewed by:
|  | Acceptance Filter Development |  | Reviewed by:
|  | Register Bank Development |  | Reviewed by:
|  | Bitstream Processor Development |  | Reviewed by:
|  | Bit Timing Module Development |  | Reviewed by:
| Stage 5: Module Verification | Wishbone IF Test Bench |  | Reviewed by: | 2020-07-22
Wishbone IF Test Results
|  | Synchronous FIFO Test Bench |  | Reviewed by:
Synchronous FIFO Test Results
|  | Tx Priority Logic Test Bench |  | Reviewed by:
Tx Priority Logic Test Results
|  | Acceptance Filter Test Bench |  | Reviewed by:
Acceptance Filter Test Results
|  | Register Bank Test Bench |  | Reviewed by:
Register Bank Test Results
|  | Bitstream Processor Test Bench |  | Reviewed by:
Bitstream Processor Test Results
|  | Bit Timing Module Test Bench |  | Reviewed by:
Bit Timing Module Test Results
| Stage 6: Top Level Implementation | Top Level Module Development |  | Reviewed by: | 2020-07-23
| Stage 7: Functional Verification | Top Level Test Bench |  | Reviewed by: | 2020-07-26
Top Level Test Results
| Stage 8: Sythesis and FPGA Implementation | Top Level Module Synthesis |  |  | 2020-07-29
|  | Hardware Implementation Plan |  | Reviewed by:
|  | Constraints File Generation |  | Reviewed by:
FPGA Implementation
Hardware Debugging
Hardware Implementation Results Documentation
| Stage 9: Final | Finalize Project Documentations |  |  | 2020-07-31