## Sheet1
| Milestone | Related Tasks | Completion Date
Phase 1 | Planning and Organization | Scheduling | 2020-06-29
Team Organization and Assignments
|  | Standards Development |  | Furlough 6/26/2020
| System Specifications | Submodule divisions | 2020-07-01
Functionality descriptions
| Requirements and Test Cases | Generation and Review | 2020-07-10 | Furlough 7/2/2020
Phase 2 | Module Development | Source code | 2020-07-16 | Furlough 7/6/2020
| Module Verification | Module Testbench and Review | 2020-07-22
| Top Level Implementation |  | 2020-07-23
| Functional Verification | Top Level Testbench and Review | 2020-07-27
| Synthesis and Hardware Implementation |  | 2020-07-29
| Final |  | 2020-07-31